## Basic Template
|  |  |  | Project Leader: |  | Bryan Spahr |  | Project: |  | Recovery | [10 empty] | Date 02/22/2014
Project Objective: Create an awesome survival horror game, taking place in space.
Objectives |  |  |  |  | Major Tasks |  |  | Project Completed By: 05/09/2014 | [10 empty] | Owner
O |  |  |  | 1 | Storyboards completed |  |  | O | [10 empty] | A | B
O |  |  |  | 2 | Gameplay, UI, powerups, feature set defined |  |  | O | [10 empty] | A | B | B
| O |  |  | 3 | Initial graphical asset created (level 1, enemy 1, models) |  |  | O |  | O | [9 empty] | A | A | A | A | A
| O |  |  | 4 | Mid semester graphical asset created (level 1 finished, enemy finished) | [5 empty] | O | [8 empty] | A | A | A | A | A
|  | O |  | 5 | Final graphical asset created | (all models completed) | [10 empty] | O |  |  | A | A | A | A | A
| O |  |  | 6 | Initial audio (SFX, Character Dialog) | [11 empty] | O |  | A
| O |  |  | 7 | Mid semester audio completed | (SFX, Character Dialog) |  |  |  |  | O | [7 empty] | A
|  | O |  | 8 | Final audio completed | (SFX, Character Dialog) | [10 empty] | O |  | A
| O | O |  | 9 | Main game finite state machine created |  |  | O | [11 empty] | A
| O | O |  | 10 | Initial user interface created | [11 empty] | O |  | A
| O | O |  | 11 | Final user interface created | [11 empty] | O |  | A
|  | O |  | 12 | Initial Enemy 1 FSM and AI |  |  | O |  | O | [10 empty] | A
|  | O |  | 13 | Initial Enemy 2 FSM and AI | [7 empty] | O
|  | O |  | 14 | initial Enemy 3 FSM and AI | [7 empty] | O
|  |  |  | 15 | MIDTERM DEMO | [5 empty] | O | [7 empty] | A | B | B
|  | O |  | 16 | Textures for Models completed | [9 empty] | O |  |  |  | A | B | B
|  | O |  | 17 | Second level initiated | [6 empty] | O | [7 empty] | A
|  | O |  | 18 | Second level completed | [9 empty] | O |  |  |  |  | A
|  | O |  | 19 | Boss Initial implementation | [7 empty] | O | [5 empty] | A |  | A |  | A | A
|  | O |  | 20 | Boss Final implementation | [10 empty] | O |  |  | A |  | A |  | A | A
|  |  | O | 21 | Playtesting among developers |  |  |  |  | O |  |  | O |  |  | O |  |  | A | A | A
|  |  | O | 22 | Midterm powerpoint completed | [5 empty] | O | [7 empty] | A | B | B
|  |  | O | 23 | Final powerpoint completed | [11 empty] | O |  | A | B | B
| O |  |  | 24 | Web site updated |  |  | O |  | O |  |  | O |  |  | O |  |  | A
|  | O |  | 25 | FINAL DEMO | [11 empty] | O |  | A
| O | O | O | 26 | Ammo System | [11 empty] | O |  | A
| O | O |  | 27 | Health System | [11 empty] | O |  | A
|  | O |  | 28 | Final Enemy Completed | [11 empty] | O |  |  |  | A
| O | O |  | 29 | Level Lighting | [12 empty] | O | A
# People working on the project:
Create design | Build Midterm Demo | Final Demo | Playtest and tune |  |  |  |  | 02/28 | 03/07 | 03/14 | 03/21 | 03/28 | 04/04 | 04/11 | 04/18 | 04/25 | 05/02 | 05/07 | Bryan Spahr | Adrian Campos | Shanon Mathai | Babak Shahian | Kylie Adkins | Jessica Candebat
[14 empty] | O | expected task activity here |  |  |  |  | A = primary owner
[14 empty] | O | no progress or stuck |  |  |  |  | B = secondary owner
[14 empty] | O | in progress
[14 empty] | O | completed
Adapted from OPPM: www.onepageprojectmanager.com